## Summary
| Issues Reported | Issues - Work in Progress | On Requirements | Out of Scope | Closed
Estore | 37 | 11 | 2 | 4 | 21
CSC | 18 | 7 | 0 | 0 | 10
Mobile | 15 | 15 | 0 | 0 | 0
Total | 70 | 33 | 2 | 4 | 31

## Summ Issues eStore
Issue No. | Description | Reporter | Reported | Criticality | Due Date | Status | Owner | Comments | Additional Comments | Comments with business | 2016-08-16 | 2016-08-23 | 2016-08-26 | 2016-08-29 | 2016-08-30
1 | Some words on eStore that should be shown in bold font, links are not shown properly | Item File | 2016-07-26 | Medium | 2016-07-27 | Not in requirement | Oscar / Arturo | For ATG Estore we display the details as we received in the Enrichment and Facet feed. Since the details n the feed received with Simple text, hence the same is displayed on Estore. | This is not an issue as it is not a part of the requirement. | Raul will Review with the team in charge (oscar) . This was reviewed with business and this will be include in next release once is a new requirement | parking lot | Provide review status. ETA: 25-Ago (arturo y Raul) | Tendremos estatus al regreso de Arturo | No se ha platicado con Arturo y falta feed texto
2 | Some items are showing the promotion icons twice | Sol | 2016-07-26 | Medium | 2016-07-27 | Closed | Walmex | Two promotions are active for the same product : 00000347371 and 00000347372. Hence 2 images are displayed on Estore | This is due to wrong mapping of promotions to the UPC | Review scenarios to have an automatically process
3 | After typing in the user and password (incorrectly) the user account is not getting blocked after 3 times | Chris | 2016-07-26 | Medium | 2016-07-27 | Closed |  | This as per the requirements. User account should not get blocked after invalid retires | This is not an issue as it is not a part of the requirement. | Closed
4 | You enter product lines and leaving huge | Amado | 2016-07-26 |  | Not Available | Duplicate | Wipro | This is also observed when #5 is seen | This issue is a part of issue #5.
5 | You can not click on the links menu | Amado | 2016-07-26 |  | 2016-09-12 | Re-Opened | Oracle/Wipro | Work In Progress. Oracle SR is raised. 29: AUG Fix is deployed in Production 30 AUG: We were able to reproduct the issue, but on Page re-load the issue is not seen. |  | Oracle/Wipro to Provide an ETA |  | Sttoper, Raul will provide ETA on 24 Ago. Status 24-Aug: There is still in progress no ETA yet | There are no new status | Retest today and it's OK
6 | Today it continues to change the image of red delicious apple in PDP | Amado | 2016-07-26 |  | 2016-09-05 | Work in Progress | Walmex/Oscar | Issue with the set of images received in the image feed for this Product. Already discussed with Oscar | Review with Oscar this point, and escalate. Deparment,family and fineline | Review with Oscar this point, and escalate. Deparment,family and fineline | imagen de familia están en centinel. Extración masiva de universo de imagen de Centinel. Revisar con Roberto Perez quien sube las imágenes. Y después regresamos con Oscar para que se carguen automáticamente. Oscar da la fecha final | Solution will be on 26-Ago | Confirma con Oscar liberación y al final del día confirma entregable | Retest today and it is NOT working properly
7 | I can not set the jump grams in weighable products | Amado | 2016-07-26 |  | 2016-07-27 | Not in requirement |  | Jump is by default 50 grms – as per the requirements. Inorder to have a jump value other than 50, team should configure the Minimum and Average weight accordingly | This is not an issue and was explained to the business team | this is a Feed issue, this will be reviewed with Perla and wipro | New requirement, for review. Revisar con Perla Palacios, para que no se sobre escriba la información desde host. | Raul will review with Perla and Rodrigo, statun on 24-Aug. Status Aug 24: Rodrigo Larios said if this requirement needs to do changes in the feed will take 2 weeks for all implementation cycle. | There are no new status | There are no new status
8 | They were set minimums and maximums for some time, but tell us that if there is a new SKU for UPC that is already configured , you must manually configure this new SKU | Amado | 2016-07-26 |  | 2016-07-27 | Not in requirement |  | This is as per the requirements. We need to configure the Minimum and Average weight at the SKU. | This is not an issue and was explained to the business team | this is a Feed issue, this will be reviewed with Perla and wipro | New requirement, for review. Wipro will review this again | Raul will review status with Perla on 24-Aug. Technical team needs to review this requirement and provide an ETA, today this will be done manually, for business this is not a good solution | There are no new status | There are no new status
9 | Links created show you items that do not correspond | Amado | 2016-07-26 |  | 2016-08-05 | Closed | Walmex | Endeca patch was deployed on 05 AUG in Production. Awaiting walmart team to test and confirm if this issue can be closed | Patch installed in Production Env. No exception happened during staging baseline indexing. Under observation, will be closed once business user confirms. | Is already fixed, business will confirm
10 | Hay artículos que tienen leyenda de Pocas Piezas, ¿cómo se define que esta leyenda se pinte? | Vianey | 2016-07-27 | Medium |  | Closed |  | Details are shared in the Attached email. Based on the Product Type, TH1, TH2 and rules defined Product will be displayed as ‘Pocas Piezas’ or ‘No Disponible’ | This is not an issue and was a request for understanding the concepts which was clarified | Closed by Business
11 | Nos pasó a varios que tienes que estar borrando cookies para que puedas ver banners y carruseles | Amado | 2016-07-27 | High |  | Duplicate |  | It looks to be issue with the PageServer Cache component for taxonomy. Team is working on the issue to understand the root cause and the fix. | This issue is a follow up on issue #5.
12 | De liga creada se ven los artículos pero algunos no muestran foto en PLP pero si en PDP | Rocio | 2016-07-27 | High |  | Duplicate | Walmex | Issue with the set of images received in the image feed for this Product. Already discussed with Oscar | This issue is a part of issue #6.
13 | Hay artículos con la leyenda no disponible, ¿cuál es la regla para que se pinte esta leyenda? | Vianey | 2016-07-27 | Medium |  | Closed |  | Details are shared in the Attached email. Based on the Product Type, TH1, TH2 and rules defined Product will be displayed as ‘Pocas Piezas’ or ‘No Disponible’ | This is not an issue and was a request for understanding the concepts which was clarified
14 | Al dar click a un no disponible, manda pantalla de Banner/ Producto no encontrado |  | 2016-07-27 | Medium | 2016-09-01 | Ready For Retest | Walmex | On click of No disponible Product will not navigate to PDP page with producto no encontrado. We should not be seeing this issue today. When checked for the same Product shared in the PPT, product is now not listed in Search Listing page as well. | This issue was not seen when checked and was not reproducible by the business team |  |  | Reopen issue, is still with same beahaivor- 24 Ago | There are no new status | Retest today, issue is was not replicate, need business approval for closing
15 | Busqueda de papel de baño y salen otros artículos | Vianey | 2016-07-27 | High |  | Closed | Walmex | Search tuning to be taken care
16 | I looked up for M&M's, there's 4 results but none are shown on PLP | Raúl / Juls | 2016-07-28 | High |  | Closed | Walmex/Geovanni | This was due to the Search configurations changed in Production Endeca. Configuratiosna are now corrected, we should not be having this issue now | Review in Endeca |  |  | Next status on 24-Ago by Geovanni. Status Aug-24: this issue is still SR open | There are no new status | There are no new status | Closed by Geovanni
17 | UPC: 00780432021408 does not have a photo (on current site it does). Still on ATG instead of showing the walmart spark, we're showing the superama logo. | Vianey | 2016-07-28 | High |  | Duplicate | Walmex | Issue with the set of images received in the image feed for this Product. Already discussed with Oscar | This issue is a part of issue #6. Oscar is working on this issue |  | Open by bussines
18 | I add items into the cart, then remove them from it and the cart is not decreasing the total amount, later I add new items and the cart is not adding to the total amount correctly | Juls | 2016-07-28 | High |  | Closed | Walmex | Issue is fixed and available in Production Env | This is closed as per the verbal confirmation by Amado
19 | Based on our understanding of the recommendations functionality: if there's only a recommendation created to a family on the whole hierarchy, the lower levels would inherit that recommendation. It is not working that way | Raul | 2016-07-29 | High |  | Closed | Walmex | Yes the understanding is correct. if there's only a recommendation created to a family on the whole hierarchy, the lower levels would inherit that recommendation, Provided property 'Default Parent Category' is mapped correctly in BCC at Each Level - Department, Family, fineline and Product. Suspect the issue is seen in case where the Default Parent category is not mapped correct. But for further analysis we need the data points - Family where recommendations were set. Finelin and Product details (Sample) where Recommendatios are not getting displayed
20 | Real order is created #1002780155 (18576185), customer never got email notification | Sol | 2016-08-01 | High | 2016-09-07 | Work in Progress | Walmex/Benjamin | Seems to be some issue with sender domain name used in production. Currently the Domain configured is ‘walmex.spitfire@walmart.com.mx’. Please let us know the Sender email can be configured for End user and for Support emails. In QA it is super@walmart.com | These configuration changes are made and it looks to be closed. Need a confirmation from the business team |  |  | Next status on 24-Aug . Status 24-Aug: This issue will be fixed next Aug-29th | There are no new status | There are no new status
21 | Brand facet is not showing properly, as not all brands are visible, once the last visible brand is selected another one appear below that one, this may need to be validated accross different browsers to see if the facet is not being displayed correctly on certainly scenarios and/or browsers | Vianey | 2016-08-01 | Medium |  | Closed | Walmex | Checked and found the issue is with endeca configuration . Maximum refinements for brand is configured as 10 in production. Changed the value to 200 in QA and it lists all the brands. So to fix this is production, shall we modify the same in endeca? | These configuration changes are made and it looks to be closed. Need a confirmation from the business team
22 | When an order is paid using PayPal eStore is not allowing the payment. | Veronica | 2016-08-09 | High | 2016-09-12 | Not implemented | Walmex/Pedro | Production Env is currently connected to Paypal SandBox Instance. Paypal Production ENV will be available only after SRCR approval. During this time, Walmex team need to create the profiles in SandBox env for testing |  |  |  | Implementation will be after 29-Aug | There are no new status | There are no new status
23 | On PLP some images has different size | Rocio | 2016-08-11 | Medium |  | Duplicate | Walmex | We have not received the proper image size in the product image feed. Oscar/team need to correct the image size in the Product Image Feed
24 | Promotion Banner Timer is not working properly | Elizabeth | 2016-08-16 | High |  | Closed | Walmex | Promotion Banner Timer is not working, evidence is attached in a separate email 29 AUG: Deployed the Fix in Prodcutuion. Please Verify |  |  |  | Next Status 24-Aug. Status 24-Aug: This will be fixed on next deployment Aug 26th | There are no new status | Retest today, has same status, it si NOT working properly | closed by business
25 | Personal Care section is not shown on eStore | Elizabeth | 2016-08-17 | High |  | Closed | Walmex/Elizabeth | Request Team to select the query again Endeca Experience Manager for this Fineline. Srinivas/Martin can help here.
26 | Images has different size | Vianey | 2016-08-17 | High |  | Duplicate |  | Work In Progress. Oracle SR is raised. Duplicate as #5
27 | When PayPal is selected as payment method, the application redirects to a wrong page | Amado | 2016-08-17 | High |  | Closed | Walmex | Need to understand more on the Flow user has taken. As of now, seems not to be an issue. Martin will check with Amado for the closure | It is the functionality of 'Enable Quick purchase with PayPal'
28 | Item is located in wrong catalog | Amado | 2016-08-18 | High | 2016-09-05 | Work in Progress | Walmex/Felix and Perla Palacios | evidence is attached in a separate email | Product status received from Enrichment feed was Blank. Hence the product is not indexed and displayed on Estore. Inorder to get the Product displayed on Estore, We need to update the Product Status |  |  | Next Status 24-Aug. Status 24-Aug: Enrichment feed needs to send to a particular product, is still in progress | There are no new status | There are no new status
29 | review functionality required by business | Amado | 2016-08-23 | High |  | New requirements | Walmex | There are functionality that business wants to include in next releases, this will be reviewed by functional team. ETA: 26-Ago |  |  |  |  | There are no new status | List requested functionalities
30 | If I capture in my eStore comments in order if printed correctly, but are not displayed in the application store in the comments field of the order | Amado | 2016-08-23 | High | 2016-09-14 | Work in Progress | Walmex / Rodrigo and Adrian, Raul Tapia | Want SE team to check and confirm why the comments are not printed in the customer print |  |  |  |  | Martin is reviewing the issue, provide an answer next Aug 29th | There are no new status
31 | Crear Cuenta. • When you press the button “Crear mi cuenta” intermittently, without entering the e-mail, the system allows passing the register form. • The system allows to pass at the registration form, when you add an e-mail with invalid form, for example: "-----@---.com" • The system doesn’t limit the characters in the e-mail area. • The system doesn’t allow realizing a search from the Login/Create Account screen. • The system allows saving a new direction without specifying your preference store, the system should send to the user, a validation message to the capture of this area. • The system allows to register an account with an invalid phone, for example "1111111111". • The system allows to register an account with an extension phone, for example "1111111111". • The system allows to register an account with an cell phone, for example "1111111111". • The system doesn’t limit the password area like in the production actual version. In the actual system the password must have from 8 to 16 characters. • The system doesn’t limit the extension area like in the actual production version. In the actual system, the extension must have 5 digits. • The system doesn’t limit the cell phone area like in the actual production version. In the actual system, the extension must have 10 digits. • The system allows adding spaces before adding the names facts in the area and these spaces have to reflect in the data edition. • The system allows adding spaces before adding the last name data area, and these spaces have to reflect in the data edition. • When you select the "VER TÉRMINOS Y CONDICIONES" link, in the register form of a new account, the system shows the label "??? profile.termsandconditions.text ???". | Miguel | 2016-08-25 | High |  | As per requirements | Wipro | • The system allows adding spaces before adding the last name data area, and these spaces have to reflect in the data edition. The point highlighted in red needs an additional analysis. It does not affects any functionality. But just to know if there is any additional imporvements that can be done.
32 | Mis Listas. • A lot of of my actual features list didn’t inherit, for example: "Copiar artículos de esta lista a", "Imprimir", "Exportar a excel", "Crear lista". • When add a product to cart, the system shows the message “Superó la cantidad permitida”. • When you rename a list with special characters, the system doesn’t show the list Detail. | Miguel | 2016-08-25 | High |  | As per requirements | Wipro | • When you rename a list with special characters, the system doesn’t show the list Detail. The point highlighted in red needs a fix. |  |  |  |  | Martin is reviewing the issue, provide an answer next Aug 29th | Revisar con Miguel los caracteres y si es stopper
33 | Home. • The system doesn’t adapt correctly to a desktop screen, the Chrome version is: 46.0.2490.80 m | Miguel | 2016-08-25 | Medium | 2016-09-01 | Closed | Walmex/Miguel´s team | This was not reproducible with the same chrome version during the meeting. Team to share further details on how to reproduce this issue. |  |  |  |  | miguel's team will send screenshot, once the issue is not able to reproduce | Se sigue trabajando, no hay fecha
34 | Salsas Caseras category has issues again, cosmetic line is into this category, it is a big mistake | Amado | 2016-08-26 | High | 2016-09-02 | Work in Progress | Walmex/Carolina's team | Added atachment | Carolina's team to confirm if the mapping of these products were done right in BCC. |  |  |  | Sends issue to wipro, we will have first answer next Aug 29th | already review with Juliana, she will provide status
35 | Into Home header shows additional characters (strange characters) | Raul Fernando | 2016-08-29 | High | 2016-09-01 | Ready For Retest | Walmex/Amado/Wipro | Added atachment 30 AUG: We have tried replicating the issue, but failed. We request Amado to show the isus eto Srini/Sudeep as soon as it is seen, meanwhile wipro team will try to reproduce in production
36 | there are more items in ATG catalog than current system Catalog | Amado | 2016-09-01 | High | 2016-09-12 | Work in Progress | Walmex/Aamdo
37 | Deploys to Endeca Production is not working properly | Elizabeth | 2016-09-02 | High | 2016-09-12 | Monitoring | Wipro / Oracle
11
,

## Summ Issues CSC
Issue No. | Description | Reporter | Reported | Criticality | Due Date | Status | Owner | Comments | additional Comments | Comments with business | 2016-08-23
1 | "Recoge en tienda" Or pick up at the store is not going through if we select the option. | Mario | 2016-08-15 | High |  | Closed | Jesus | Service is not available for our customer and freezes at the time that we try to select a slot | To be Retested in IE8 and confirm back Also please note Agent needs to select the Store option from the Shipping page to see Store Pickup payment options on later screens
2 | Payment options are retricted to one per order | Mario | 2016-08-15 | High |  | Closed | Walmex/Arturo | Previous CRM aloud us to select diferent payment opts on the order, per customer request. | Partial payment method is not a part of the requirement. Refer JIIRA ID: | There should be option for multiple payments. | Parking Lot. Se incluye el requerimiento para un release posterior
3 | The bill options are not correct. | Mario | 2016-08-15 | High |  | Closed | Walmex/Arturo | Extra information is required whenever the customer ask for the bill , the options are incorrect. | Please Note billing address or invoice address was not part of the spitfire requirements. Refer JIIRA ID: | Need to recheck on the requirements as this is really necessary.
4 | Systems is experimenting slow behaivor | Mario | 2016-08-15 | High | 2016-09-12 | Work in Progress | Walmex/Javier | Takes from 5 to 15 minutes to actually change from screen to screen. | 19 AUG: When checked the CSC performance from the Location where martin/Srini are available, CSC page is loading in less than 5 seconds. We request raul/Javier to check on the Walmart Network from Mario's location |  | Network team is working to have better network performance. ETA: 31-Aug
5 | Data from a existing regular customers is no showing up | Valeria | 2016-08-15 | High |  | Re-opened | Jesus | The store can´t identify a test order from a real one | Unable to search users with First name and Last Name fields. | Jesus to share the db related info on Current Customer care service. | review deep detail
6 | The link is not working through internet explorer | Javier | 2016-08-15 | High |  | Duplicate/Work in Progress |  | Use work , no is not and we are currently using Chrome to do the testing. | The issue still persist. We assume that this is due to the slowness of the network. Duplicated to issue#4
7 | Surcharge from home delivery it´s wrong | Mario y Javier | 2016-08-15 | High |  | Closed | Walmex | Te surcharge is $49 pesos and we currently have $44 pesos, shoulkd be changed. | This is functioning properly as per the feed received. | Martin to share datails from Perla | do more testing. Jesus send the test 24-Aug
8 | The catalog is incomplete. | Mario y Javier | 2016-08-15 | High | 2016-09-02 | Closed | Jesus | Basic stuff is not available , regular products that our customers request | Need details on product and stores. |  | Review deep detail with wipro. 24-Aug
9 | Image from the Item isn´t available | Mario y Javier | 2016-08-15 | High |  | Closed | Walmex | Image shpuld be avaible to comply with the right Item , entire order could be cancel if we send the wrong products | The walmart default images are getting displayed for the UPC for which images feeds are not available. |  | Jesus will share the UPCs where there is discrepancy between eStore and CSC. Solution on 26-Aug
10 | We cant apply the promotions | Mario y Javier | 2016-08-15 | High | 2016-09-02 | Closed | Jesus | We add a promo that is not reflected at the end. | Need few UPC examples to check if Business team has created the promotion in BCC We checked on the few items with promotions and were able to see Promotion getting applied | The products which Jesus has shared has promotion in Current Customer care centre and interim site. But they are not coming via feeds and they are not created in BCC. | Jesus to retest once Amado shares the list of promotions created. 24-Aug
11 | Current promos are not avalaible | Mario y Javier | 2016-08-15 | High | 2016-09-02 | Closed | Jesus | Affect the cross sell thart we coul apply on the every call if is not visible for the sales rep. | We display the cross sell promotions in Full cart page - 'Examinar todos las Promociones'. This is as per CSC Out of the Box. Martin/Srini can help more on this |  | Amado envia ejemplos a Jesus y se vuelve a probar. 24-Aug
12 | Comment on the order are not avialble just until the order its printed | Mario y Javier | 2016-08-15 | High |  | Work in Progress | Walmex/Super Entrega | The store can´t identify a test order from a real one | The comments (Order level and order line comments) are not received at the store side We see the item level and order level comments are available in the order. Can SE team check and confirm why the comments are not printed in Customer print |  | Jesus to retest with another order and confirm on the issues with respect to the comments. 24-Aug
13 | Order is not availbale | Mario y Javier | 2016-08-15 | High |  | Closed | Walmex | Previous CRM aloud us to cuantify and observe previous orders set up by every users. | 22 AUG: Please refer the screen shot shared ,where the CSC agent can search for the orders with different status ad dates | Need to know of the option to see all the orders placed for a particular day by specific agent | This is not an out of the box functionality and it is not a part of the requirement.
14 | CSC have the wrong Postal codes | Mario y Javier | 2016-08-15 | High | 2016-09-02 | Ready for retest | Walmex/Jesus | We select a regular location to send an order that won´t go through caude is says that we have no coverage on the area | 19 AUG: Need Business team to check on the Zipcode-Store-Colony-Amt id feed provided to us. As there as no Store received for the zipcode in issue hence we display this error on CSC |  | Provide status 24-Aug
15 | Uploaded catalog is not working properly | Mario y Javier | 2016-08-15 | High | 2016-09-02 | Ready for retest | Walmex/Jesus | Regular item as milk already uploaded on the system is not working for us, we cant added tyo the shoipping cart | We see Keyboard Search is working. Please verify in IE8
16 | All the items are as not available | Mario y Javier | 2016-08-15 | High |  | Closed | Walmex/Jesus | Orders can´t be made | We see Keyboard Search is working. Please verify in IE8
17 | The weighing is not right | Mario y Javier | 2016-08-15 | High | 2016-09-02 | Ready for retest | Walmex/Arturo | We add a certain weight and the system change to a diferent one . | This is as per requirement of minimum weight and average weight. Business to comment on the cases if the customer is so specific on the quantity he/she demands |  | Jesus envía un ejemplo para seguir el issue 24-Aug
18 | We add certain amount of items and at the end , we are missing some of them | Mario y Javier | 2016-08-15 | High |  | Closed | Walmex | We add certain amount of items and at the end , we are missing some of them | This is as per requirement of PIP |  | Validar las reglas de host con Perla
10

## Summ Req eStore
Issue No. | Description | Reporter | Reported | Criticality | Due Date | Status | Owner | Comments | Additional Comments | Comments with business | 2016-08-16 | 2016-08-23 | 2016-08-26 | 2016-08-29 | 2016-08-30
1 | Some words on eStore that should be shown in bold font, links are not shown properly | Item File | 2016-07-26 | Medium | 2016-07-27 | Not in requirement | Oscar / Arturo | For ATG Estore we display the details as we received in the Enrichment and Facet feed. Since the details n the feed received with Simple text, hence the same is displayed on Estore. | This is not an issue as it is not a part of the requirement. | Raul will Review with the team in charge (oscar) . This was reviewed with business and this will be include in next release once is a new requirement | parking lot | Provide review status. ETA: 25-Ago (arturo y Raul) | Tendremos estatus al regreso de Arturo | No se ha platicado con Arturo y falta feed texto
2 | Some items are showing the promotion icons twice | Sol | 2016-07-26 | Medium | 2016-07-27 | Closed | Walmex | Two promotions are active for the same product : 00000347371 and 00000347372. Hence 2 images are displayed on Estore | This is due to wrong mapping of promotions to the UPC | Review scenarios to have an automatically process
3 | After typing in the user and password (incorrectly) the user account is not getting blocked after 3 times | Chris | 2016-07-26 | Medium | 2016-07-27 | Closed |  | This as per the requirements. User account should not get blocked after invalid retires | This is not an issue as it is not a part of the requirement. | Closed
4 | You enter product lines and leaving huge | Amado | 2016-07-26 |  | Not Available | Duplicate | Wipro | This is also observed when #5 is seen | This issue is a part of issue #5.
5 | You can not click on the links menu | Amado | 2016-07-26 |  | Not Available | Re-Opened | Oracle/Wipro | Work In Progress. Oracle SR is raised. 29: AUG Fix is deployed in Production 30 AUG: We were able to reproduct the issue, but on Page re-load the issue is not seen. |  | Oracle/Wipro to Provide an ETA |  | Sttoper, Raul will provide ETA on 24 Ago. Status 24-Aug: There is still in progress no ETA yet | There are no new status | Retest today and it's OK
6 | Today it continues to change the image of red delicious apple in PDP | Amado | 2016-07-26 |  | 2016-07-27 | Work in Progress | Walmex/Oscar | Issue with the set of images received in the image feed for this Product. Already discussed with Oscar | Review with Oscar this point, and escalate. Deparment,family and fineline | Review with Oscar this point, and escalate. Deparment,family and fineline | imagen de familia están en centinel. Extración masiva de universo de imagen de Centinel. Revisar con Roberto Perez quien sube las imágenes. Y después regresamos con Oscar para que se carguen automáticamente. Oscar da la fecha final | Solution will be on 26-Ago | Confirma con Oscar liberación y al final del día confirma entregable | Retest today and it is NOT working properly
7 | I can not set the jump grams in weighable products | Amado | 2016-07-26 |  | 2016-07-27 | Not in requirement |  | Jump is by default 50 grms – as per the requirements. Inorder to have a jump value other than 50, team should configure the Minimum and Average weight accordingly | This is not an issue and was explained to the business team | this is a Feed issue, this will be reviewed with Perla and wipro | New requirement, for review. Revisar con Perla Palacios, para que no se sobre escriba la información desde host. | Raul will review with Perla and Rodrigo, statun on 24-Aug. Status Aug 24: Rodrigo Larios said if this requirement needs to do changes in the feed will take 2 weeks for all implementation cycle. | There are no new status | There are no new status
8 | They were set minimums and maximums for some time, but tell us that if there is a new SKU for UPC that is already configured , you must manually configure this new SKU | Amado | 2016-07-26 |  | 2016-07-27 | Not in requirement |  | This is as per the requirements. We need to configure the Minimum and Average weight at the SKU. | This is not an issue and was explained to the business team | this is a Feed issue, this will be reviewed with Perla and wipro | New requirement, for review. Wipro will review this again | Raul will review status with Perla on 24-Aug. Technical team needs to review this requirement and provide an ETA, today this will be done manually, for business this is not a good solution | There are no new status | There are no new status
9 | Links created show you items that do not correspond | Amado | 2016-07-26 |  | 2016-08-05 | Closed | Walmex | Endeca patch was deployed on 05 AUG in Production. Awaiting walmart team to test and confirm if this issue can be closed | Patch installed in Production Env. No exception happened during staging baseline indexing. Under observation, will be closed once business user confirms. | Is already fixed, business will confirm
10 | Hay artículos que tienen leyenda de Pocas Piezas, ¿cómo se define que esta leyenda se pinte? | Vianey | 2016-07-27 | Medium |  | Closed |  | Details are shared in the Attached email. Based on the Product Type, TH1, TH2 and rules defined Product will be displayed as ‘Pocas Piezas’ or ‘No Disponible’ | This is not an issue and was a request for understanding the concepts which was clarified | Closed by Business
11 | Nos pasó a varios que tienes que estar borrando cookies para que puedas ver banners y carruseles | Amado | 2016-07-27 | High |  | Duplicate |  | It looks to be issue with the PageServer Cache component for taxonomy. Team is working on the issue to understand the root cause and the fix. | This issue is a follow up on issue #5.
12 | De liga creada se ven los artículos pero algunos no muestran foto en PLP pero si en PDP | Rocio | 2016-07-27 | High |  | Duplicate | Walmex | Issue with the set of images received in the image feed for this Product. Already discussed with Oscar | This issue is a part of issue #6.
13 | Hay artículos con la leyenda no disponible, ¿cuál es la regla para que se pinte esta leyenda? | Vianey | 2016-07-27 | Medium |  | Closed |  | Details are shared in the Attached email. Based on the Product Type, TH1, TH2 and rules defined Product will be displayed as ‘Pocas Piezas’ or ‘No Disponible’ | This is not an issue and was a request for understanding the concepts which was clarified
14 | Al dar click a un no disponible, manda pantalla de Banner/ Producto no encontrado |  | 2016-07-27 | Medium |  | Ready For Retest | Walmex | On click of No disponible Product will not navigate to PDP page with producto no encontrado. We should not be seeing this issue today. When checked for the same Product shared in the PPT, product is now not listed in Search Listing page as well. | This issue was not seen when checked and was not reproducible by the business team |  |  | Reopen issue, is still with same beahaivor- 24 Ago | There are no new status | Retest today, issue is was not replicate, need business approval for closing
15 | Busqueda de papel de baño y salen otros artículos | Vianey | 2016-07-27 | High |  | Closed | Walmex | Search tuning to be taken care
16 | I looked up for M&M's, there's 4 results but none are shown on PLP | Raúl / Juls | 2016-07-28 | High |  | Closed | Walmex/Geovanni | This was due to the Search configurations changed in Production Endeca. Configuratiosna are now corrected, we should not be having this issue now | Review in Endeca |  |  | Next status on 24-Ago by Geovanni. Status Aug-24: this issue is still SR open | There are no new status | There are no new status | Closed by Geovanni
17 | UPC: 00780432021408 does not have a photo (on current site it does). Still on ATG instead of showing the walmart spark, we're showing the superama logo. | Vianey | 2016-07-28 | High |  | Duplicate | Walmex | Issue with the set of images received in the image feed for this Product. Already discussed with Oscar | This issue is a part of issue #6. Oscar is working on this issue |  | Open by bussines
18 | I add items into the cart, then remove them from it and the cart is not decreasing the total amount, later I add new items and the cart is not adding to the total amount correctly | Juls | 2016-07-28 | High |  | Closed | Walmex | Issue is fixed and available in Production Env | This is closed as per the verbal confirmation by Amado
19 | Based on our understanding of the recommendations functionality: if there's only a recommendation created to a family on the whole hierarchy, the lower levels would inherit that recommendation. It is not working that way | Raul | 2016-07-29 | High |  | Closed | Walmex | Yes the understanding is correct. if there's only a recommendation created to a family on the whole hierarchy, the lower levels would inherit that recommendation, Provided property 'Default Parent Category' is mapped correctly in BCC at Each Level - Department, Family, fineline and Product. Suspect the issue is seen in case where the Default Parent category is not mapped correct. But for further analysis we need the data points - Family where recommendations were set. Finelin and Product details (Sample) where Recommendatios are not getting displayed
20 | Real order is created #1002780155 (18576185), customer never got email notification | Sol | 2016-08-01 | High |  | Work in Progress | Walmex/Benjamin | Seems to be some issue with sender domain name used in production. Currently the Domain configured is ‘walmex.spitfire@walmart.com.mx’. Please let us know the Sender email can be configured for End user and for Support emails. In QA it is super@walmart.com | These configuration changes are made and it looks to be closed. Need a confirmation from the business team |  |  | Next status on 24-Aug . Status 24-Aug: This issue will be fixed next Aug-29th | There are no new status | There are no new status
21 | Brand facet is not showing properly, as not all brands are visible, once the last visible brand is selected another one appear below that one, this may need to be validated accross different browsers to see if the facet is not being displayed correctly on certainly scenarios and/or browsers | Vianey | 2016-08-01 | Medium |  | Closed | Walmex | Checked and found the issue is with endeca configuration . Maximum refinements for brand is configured as 10 in production. Changed the value to 200 in QA and it lists all the brands. So to fix this is production, shall we modify the same in endeca? | These configuration changes are made and it looks to be closed. Need a confirmation from the business team
22 | When an order is paid using PayPal eStore is not allowing the payment. | Veronica | 2016-08-09 | High |  | Not implemented | Walmex/Pedro | Production Env is currently connected to Paypal SandBox Instance. Paypal Production ENV will be available only after SRCR approval. During this time, Walmex team need to create the profiles in SandBox env for testing |  |  |  | Implementation will be after 29-Aug | There are no new status | There are no new status
23 | On PLP some images has different size | Rocio | 2016-08-11 | Medium |  | Duplicate | Walmex | We have not received the proper image size in the product image feed. Oscar/team need to correct the image size in the Product Image Feed
24 | Promotion Banner Timer is not working properly | Elizabeth | 2016-08-16 | High |  | Closed | Walmex | Promotion Banner Timer is not working, evidence is attached in a separate email 29 AUG: Deployed the Fix in Prodcutuion. Please Verify |  |  |  | Next Status 24-Aug. Status 24-Aug: This will be fixed on next deployment Aug 26th | There are no new status | Retest today, has same status, it si NOT working properly | closed by business
25 | Personal Care section is not shown on eStore | Elizabeth | 2016-08-17 | High |  | Closed | Walmex/Elizabeth | Request Team to select the query again Endeca Experience Manager for this Fineline. Srinivas/Martin can help here.
26 | Images has different size | Vianey | 2016-08-17 | High |  | Duplicate |  | Work In Progress. Oracle SR is raised. Duplicate as #5
27 | When PayPal is selected as payment method, the application redirects to a wrong page | Amado | 2016-08-17 | High |  | Closed | Walmex | Need to understand more on the Flow user has taken. As of now, seems not to be an issue. Martin will check with Amado for the closure | It is the functionality of 'Enable Quick purchase with PayPal'
28 | Item is located in wrong catalog | Amado | 2016-08-18 | High |  | Work in Progress | Walmex/Felix and Perla Palacios | evidence is attached in a separate email | Product status received from Enrichment feed was Blank. Hence the product is not indexed and displayed on Estore. Inorder to get the Product displayed on Estore, We need to update the Product Status |  |  | Next Status 24-Aug. Status 24-Aug: Enrichment feed needs to send to a particular product, is still in progress | There are no new status | There are no new status
29 | review functionality required by business | Amado | 2016-08-23 | High |  | New requirements | Walmex | There are functionality that business wants to include in next releases, this will be reviewed by functional team. ETA: 26-Ago |  |  |  |  | There are no new status | List requested functionalities
30 | If I capture in my eStore comments in order if printed correctly, but are not displayed in the application store in the comments field of the order | Amado | 2016-08-23 | High |  | New | Walmex / Rodrigo and Adrian | Want SE team to check and confirm why the comments are not printed in the customer print |  |  |  |  | Martin is reviewing the issue, provide an answer next Aug 29th | There are no new status
31 | Crear Cuenta. • When you press the button “Crear mi cuenta” intermittently, without entering the e-mail, the system allows passing the register form. • The system allows to pass at the registration form, when you add an e-mail with invalid form, for example: "-----@---.com" • The system doesn’t limit the characters in the e-mail area. • The system doesn’t allow realizing a search from the Login/Create Account screen. • The system allows saving a new direction without specifying your preference store, the system should send to the user, a validation message to the capture of this area. • The system allows to register an account with an invalid phone, for example "1111111111". • The system allows to register an account with an extension phone, for example "1111111111". • The system allows to register an account with an cell phone, for example "1111111111". • The system doesn’t limit the password area like in the production actual version. In the actual system the password must have from 8 to 16 characters. • The system doesn’t limit the extension area like in the actual production version. In the actual system, the extension must have 5 digits. • The system doesn’t limit the cell phone area like in the actual production version. In the actual system, the extension must have 10 digits. • The system allows adding spaces before adding the names facts in the area and these spaces have to reflect in the data edition. • The system allows adding spaces before adding the last name data area, and these spaces have to reflect in the data edition. • When you select the "VER TÉRMINOS Y CONDICIONES" link, in the register form of a new account, the system shows the label "??? profile.termsandconditions.text ???". | Miguel | 2016-08-25 | High |  | As per requirements | Wipro | • The system allows adding spaces before adding the last name data area, and these spaces have to reflect in the data edition. The point highlighted in red needs an additional analysis. It does not affects any functionality. But just to know if there is any additional imporvements that can be done.
32 | Mis Listas. • A lot of of my actual features list didn’t inherit, for example: "Copiar artículos de esta lista a", "Imprimir", "Exportar a excel", "Crear lista". • When add a product to cart, the system shows the message “Superó la cantidad permitida”. • When you rename a list with special characters, the system doesn’t show the list Detail. | Miguel | 2016-08-25 | High |  | As per requirements | Wipro | • When you rename a list with special characters, the system doesn’t show the list Detail. The point highlighted in red needs a fix. |  |  |  |  | Martin is reviewing the issue, provide an answer next Aug 29th | Revisar con Miguel los caracteres y si es stopper
33 | Home. • The system doesn’t adapt correctly to a desktop screen, the Chrome version is: 46.0.2490.80 m | Miguel | 2016-08-25 | High |  | Pending Clarification | Walmex/Miguel´s team | This was not reproducible with the same chrome version during the meeting. Team to share further details on how to reproduce this issue. |  |  |  |  | miguel's team will send screenshot, once the issue is not able to reproduce | Se sigue trabajando, no hay fecha
34 | Salsas Caseras category has issues again, cosmetic line is into this category, it is a big mistake | Amado | 2016-08-26 | High |  | Pending Clarification | Walmex/Carolina's team | Added atachment | Carolina's team to confirm if the mapping of these products were done right in BCC. |  |  |  | Sends issue to wipro, we will have first answer next Aug 29th | already review with Juliana, she will provide status
35 | Into Home header shows additional characters (strange characters) | Raul Fernando | 2016-08-29 | High |  | Ready For Retest | Walmex/Amado/Wipro | Added atachment 30 AUG: We have tried replicating the issue, but failed. We request Amado to show the isus eto Srini/Sudeep as soon as it is seen, meanwhile wipro team will try to reproduce in production
2
,

## Summ OOE eStore
Issue No. | Description | Reporter | Reported | Criticality | Due Date | Status | Owner | Comments | Additional Comments | Comments with business | 2016-08-16 | 2016-08-23 | 2016-08-26 | 2016-08-29 | 2016-08-30 | 2016-09-05
1 | Some words on eStore that should be shown in bold font, links are not shown properly | Item File | 2016-07-26 | Medium | 2016-09-14 | Not in requirement | Oscar / Arturo | For ATG Estore we display the details as we received in the Enrichment and Facet feed. Since the details n the feed received with Simple text, hence the same is displayed on Estore. | This is not an issue as it is not a part of the requirement. | Raul will Review with the team in charge (oscar) . This was reviewed with business and this will be include in next release once is a new requirement | parking lot | Provide review status. ETA: 25-Ago (arturo y Raul) | Tendremos estatus al regreso de Arturo | No se ha platicado con Arturo y falta feed texto
2 | Some items are showing the promotion icons twice | Sol | 2016-07-26 | Medium | 2016-07-27 | Closed | Walmex | Two promotions are active for the same product : 00000347371 and 00000347372. Hence 2 images are displayed on Estore | This is due to wrong mapping of promotions to the UPC | Review scenarios to have an automatically process
3 | After typing in the user and password (incorrectly) the user account is not getting blocked after 3 times | Chris | 2016-07-26 | Medium | 2016-07-27 | Closed |  | This as per the requirements. User account should not get blocked after invalid retires | This is not an issue as it is not a part of the requirement. | Closed
4 | You enter product lines and leaving huge | Amado | 2016-07-26 |  | Not Available | Duplicate | Wipro | This is also observed when #5 is seen | This issue is a part of issue #5.
5 | You can not click on the links menu | Amado | 2016-07-26 |  | Not Available | Re-Opened | Oracle/Wipro | Work In Progress. Oracle SR is raised. 29: AUG Fix is deployed in Production 30 AUG: We were able to reproduct the issue, but on Page re-load the issue is not seen. |  | Oracle/Wipro to Provide an ETA |  | Sttoper, Raul will provide ETA on 24 Ago. Status 24-Aug: There is still in progress no ETA yet | There are no new status | Retest today and it's OK
6 | Today it continues to change the image of red delicious apple in PDP | Amado | 2016-07-26 |  | 2016-07-27 | Work in Progress | Walmex/Oscar | Issue with the set of images received in the image feed for this Product. Already discussed with Oscar | Review with Oscar this point, and escalate. Deparment,family and fineline | Review with Oscar this point, and escalate. Deparment,family and fineline | imagen de familia están en centinel. Extración masiva de universo de imagen de Centinel. Revisar con Roberto Perez quien sube las imágenes. Y después regresamos con Oscar para que se carguen automáticamente. Oscar da la fecha final | Solution will be on 26-Ago | Confirma con Oscar liberación y al final del día confirma entregable | Retest today and it is NOT working properly
7 | I can not set the jump grams in weighable products | Amado | 2016-07-26 |  | 2016-09-14 | Not in requirement |  | Jump is by default 50 grms – as per the requirements. Inorder to have a jump value other than 50, team should configure the Minimum and Average weight accordingly | This is not an issue and was explained to the business team | this is a Feed issue, this will be reviewed with Perla and wipro | New requirement, for review. Revisar con Perla Palacios, para que no se sobre escriba la información desde host. | Raul will review with Perla and Rodrigo, statun on 24-Aug. Status Aug 24: Rodrigo Larios said if this requirement needs to do changes in the feed will take 2 weeks for all implementation cycle. | There are no new status | There are no new status
8 | They were set minimums and maximums for some time, but tell us that if there is a new SKU for UPC that is already configured , you must manually configure this new SKU | Amado | 2016-07-26 |  | 2016-09-14 | Not in requirement |  | This is as per the requirements. We need to configure the Minimum and Average weight at the SKU. | This is not an issue and was explained to the business team | this is a Feed issue, this will be reviewed with Perla and wipro | New requirement, for review. Wipro will review this again | Raul will review status with Perla on 24-Aug. Technical team needs to review this requirement and provide an ETA, today this will be done manually, for business this is not a good solution | There are no new status | There are no new status
9 | Links created show you items that do not correspond | Amado | 2016-07-26 |  | 2016-08-05 | Closed | Walmex | Endeca patch was deployed on 05 AUG in Production. Awaiting walmart team to test and confirm if this issue can be closed | Patch installed in Production Env. No exception happened during staging baseline indexing. Under observation, will be closed once business user confirms. | Is already fixed, business will confirm
10 | Hay artículos que tienen leyenda de Pocas Piezas, ¿cómo se define que esta leyenda se pinte? | Vianey | 2016-07-27 | Medium |  | Closed |  | Details are shared in the Attached email. Based on the Product Type, TH1, TH2 and rules defined Product will be displayed as ‘Pocas Piezas’ or ‘No Disponible’ | This is not an issue and was a request for understanding the concepts which was clarified | Closed by Business
11 | Nos pasó a varios que tienes que estar borrando cookies para que puedas ver banners y carruseles | Amado | 2016-07-27 | High |  | Duplicate |  | It looks to be issue with the PageServer Cache component for taxonomy. Team is working on the issue to understand the root cause and the fix. | This issue is a follow up on issue #5.
12 | De liga creada se ven los artículos pero algunos no muestran foto en PLP pero si en PDP | Rocio | 2016-07-27 | High |  | Duplicate | Walmex | Issue with the set of images received in the image feed for this Product. Already discussed with Oscar | This issue is a part of issue #6.
13 | Hay artículos con la leyenda no disponible, ¿cuál es la regla para que se pinte esta leyenda? | Vianey | 2016-07-27 | Medium |  | Closed |  | Details are shared in the Attached email. Based on the Product Type, TH1, TH2 and rules defined Product will be displayed as ‘Pocas Piezas’ or ‘No Disponible’ | This is not an issue and was a request for understanding the concepts which was clarified
14 | Al dar click a un no disponible, manda pantalla de Banner/ Producto no encontrado |  | 2016-07-27 | Medium |  | Ready For Retest | Walmex | On click of No disponible Product will not navigate to PDP page with producto no encontrado. We should not be seeing this issue today. When checked for the same Product shared in the PPT, product is now not listed in Search Listing page as well. | This issue was not seen when checked and was not reproducible by the business team |  |  | Reopen issue, is still with same beahaivor- 24 Ago | There are no new status | Retest today, issue is was not replicate, need business approval for closing
15 | Busqueda de papel de baño y salen otros artículos | Vianey | 2016-07-27 | High |  | Closed | Walmex | Search tuning to be taken care
16 | I looked up for M&M's, there's 4 results but none are shown on PLP | Raúl / Juls | 2016-07-28 | High |  | Closed | Walmex/Geovanni | This was due to the Search configurations changed in Production Endeca. Configuratiosna are now corrected, we should not be having this issue now | Review in Endeca |  |  | Next status on 24-Ago by Geovanni. Status Aug-24: this issue is still SR open | There are no new status | There are no new status | Closed by Geovanni
17 | UPC: 00780432021408 does not have a photo (on current site it does). Still on ATG instead of showing the walmart spark, we're showing the superama logo. | Vianey | 2016-07-28 | High |  | Duplicate | Walmex | Issue with the set of images received in the image feed for this Product. Already discussed with Oscar | This issue is a part of issue #6. Oscar is working on this issue |  | Open by bussines
18 | I add items into the cart, then remove them from it and the cart is not decreasing the total amount, later I add new items and the cart is not adding to the total amount correctly | Juls | 2016-07-28 | High |  | Closed | Walmex | Issue is fixed and available in Production Env | This is closed as per the verbal confirmation by Amado
19 | Based on our understanding of the recommendations functionality: if there's only a recommendation created to a family on the whole hierarchy, the lower levels would inherit that recommendation. It is not working that way | Raul | 2016-07-29 | High |  | Closed | Walmex | Yes the understanding is correct. if there's only a recommendation created to a family on the whole hierarchy, the lower levels would inherit that recommendation, Provided property 'Default Parent Category' is mapped correctly in BCC at Each Level - Department, Family, fineline and Product. Suspect the issue is seen in case where the Default Parent category is not mapped correct. But for further analysis we need the data points - Family where recommendations were set. Finelin and Product details (Sample) where Recommendatios are not getting displayed
20 | Real order is created #1002780155 (18576185), customer never got email notification | Sol | 2016-08-01 | High |  | Work in Progress | Walmex/Benjamin | Seems to be some issue with sender domain name used in production. Currently the Domain configured is ‘walmex.spitfire@walmart.com.mx’. Please let us know the Sender email can be configured for End user and for Support emails. In QA it is super@walmart.com | These configuration changes are made and it looks to be closed. Need a confirmation from the business team |  |  | Next status on 24-Aug . Status 24-Aug: This issue will be fixed next Aug-29th | There are no new status | There are no new status
21 | Brand facet is not showing properly, as not all brands are visible, once the last visible brand is selected another one appear below that one, this may need to be validated accross different browsers to see if the facet is not being displayed correctly on certainly scenarios and/or browsers | Vianey | 2016-08-01 | Medium |  | Closed | Walmex | Checked and found the issue is with endeca configuration . Maximum refinements for brand is configured as 10 in production. Changed the value to 200 in QA and it lists all the brands. So to fix this is production, shall we modify the same in endeca? | These configuration changes are made and it looks to be closed. Need a confirmation from the business team
22 | When an order is paid using PayPal eStore is not allowing the payment. | Veronica | 2016-08-09 | High |  | Not implemented | Walmex/Pedro | Production Env is currently connected to Paypal SandBox Instance. Paypal Production ENV will be available only after SRCR approval. During this time, Walmex team need to create the profiles in SandBox env for testing |  |  |  | Implementation will be after 29-Aug | There are no new status | There are no new status
23 | On PLP some images has different size | Rocio | 2016-08-11 | Medium |  | Duplicate | Walmex | We have not received the proper image size in the product image feed. Oscar/team need to correct the image size in the Product Image Feed
24 | Promotion Banner Timer is not working properly | Elizabeth | 2016-08-16 | High |  | Closed | Walmex | Promotion Banner Timer is not working, evidence is attached in a separate email 29 AUG: Deployed the Fix in Prodcutuion. Please Verify |  |  |  | Next Status 24-Aug. Status 24-Aug: This will be fixed on next deployment Aug 26th | There are no new status | Retest today, has same status, it si NOT working properly | closed by business
25 | Personal Care section is not shown on eStore | Elizabeth | 2016-08-17 | High |  | Closed | Walmex/Elizabeth | Request Team to select the query again Endeca Experience Manager for this Fineline. Srinivas/Martin can help here.
26 | Images has different size | Vianey | 2016-08-17 | High |  | Duplicate |  | Work In Progress. Oracle SR is raised. Duplicate as #5
27 | When PayPal is selected as payment method, the application redirects to a wrong page | Amado | 2016-08-17 | High |  | Closed | Walmex | Need to understand more on the Flow user has taken. As of now, seems not to be an issue. Martin will check with Amado for the closure | It is the functionality of 'Enable Quick purchase with PayPal'
28 | Item is located in wrong catalog | Amado | 2016-08-18 | High |  | Work in Progress | Walmex/Felix and Perla Palacios | evidence is attached in a separate email | Product status received from Enrichment feed was Blank. Hence the product is not indexed and displayed on Estore. Inorder to get the Product displayed on Estore, We need to update the Product Status |  |  | Next Status 24-Aug. Status 24-Aug: Enrichment feed needs to send to a particular product, is still in progress | There are no new status | There are no new status
29 | review functionality required by business | Amado | 2016-08-23 | High |  | New requirements | Walmex | There are functionality that business wants to include in next releases, this will be reviewed by functional team. ETA: 26-Ago |  |  |  |  | There are no new status | List requested functionalities
30 | If I capture in my eStore comments in order if printed correctly, but are not displayed in the application store in the comments field of the order | Amado | 2016-08-23 | High |  | New | Walmex / Rodrigo and Adrian | Want SE team to check and confirm why the comments are not printed in the customer print |  |  |  |  | Martin is reviewing the issue, provide an answer next Aug 29th | There are no new status
31 | Crear Cuenta. • When you press the button “Crear mi cuenta” intermittently, without entering the e-mail, the system allows passing the register form. • The system allows to pass at the registration form, when you add an e-mail with invalid form, for example: "-----@---.com" • The system doesn’t limit the characters in the e-mail area. • The system doesn’t allow realizing a search from the Login/Create Account screen. • The system allows saving a new direction without specifying your preference store, the system should send to the user, a validation message to the capture of this area. • The system allows to register an account with an invalid phone, for example "1111111111". • The system allows to register an account with an extension phone, for example "1111111111". • The system allows to register an account with an cell phone, for example "1111111111". • The system doesn’t limit the password area like in the production actual version. In the actual system the password must have from 8 to 16 characters. • The system doesn’t limit the extension area like in the actual production version. In the actual system, the extension must have 5 digits. • The system doesn’t limit the cell phone area like in the actual production version. In the actual system, the extension must have 10 digits. • The system allows adding spaces before adding the names facts in the area and these spaces have to reflect in the data edition. • The system allows adding spaces before adding the last name data area, and these spaces have to reflect in the data edition. • When you select the "VER TÉRMINOS Y CONDICIONES" link, in the register form of a new account, the system shows the label "??? profile.termsandconditions.text ???". | Miguel | 2016-08-25 | High |  | As per requirements | Wipro | • The system allows adding spaces before adding the last name data area, and these spaces have to reflect in the data edition. The point highlighted in red needs an additional analysis. It does not affects any functionality. But just to know if there is any additional imporvements that can be done.
32 | Mis Listas. • A lot of of my actual features list didn’t inherit, for example: "Copiar artículos de esta lista a", "Imprimir", "Exportar a excel", "Crear lista". • When add a product to cart, the system shows the message “Superó la cantidad permitida”. • When you rename a list with special characters, the system doesn’t show the list Detail. | Miguel | 2016-08-25 | High |  | As per requirements | Wipro | • When you rename a list with special characters, the system doesn’t show the list Detail. The point highlighted in red needs a fix. |  |  |  |  | Martin is reviewing the issue, provide an answer next Aug 29th | Revisar con Miguel los caracteres y si es stopper
33 | Home. • The system doesn’t adapt correctly to a desktop screen, the Chrome version is: 46.0.2490.80 m | Miguel | 2016-08-25 | High |  | Pending Clarification | Walmex/Miguel´s team | This was not reproducible with the same chrome version during the meeting. Team to share further details on how to reproduce this issue. |  |  |  |  | miguel's team will send screenshot, once the issue is not able to reproduce | Se sigue trabajando, no hay fecha
34 | Salsas Caseras category has issues again, cosmetic line is into this category, it is a big mistake | Amado | 2016-08-26 | High |  | Pending Clarification | Walmex/Carolina's team | Added atachment | Carolina's team to confirm if the mapping of these products were done right in BCC. |  |  |  | Sends issue to wipro, we will have first answer next Aug 29th | already review with Juliana, she will provide status
35 | Into Home header shows additional characters (strange characters) | Raul Fernando | 2016-08-29 | High |  | Ready For Retest | Walmex/Amado/Wipro | Added atachment 30 AUG: We have tried replicating the issue, but failed. We request Amado to show the isus eto Srini/Sudeep as soon as it is seen, meanwhile wipro team will try to reproduce in production
4
,

## Summ Closed eStore
Issue No. | Description | Reporter | Reported | Criticality | Due Date | Status | Owner | Comments | Additional Comments | Comments with business | 2016-08-16 | 2016-08-23 | 2016-08-26 | 2016-08-29 | 2016-08-30
1 | Some words on eStore that should be shown in bold font, links are not shown properly | Item File | 2016-07-26 | Medium | 2016-07-27 | Not in requirement | Oscar / Arturo | For ATG Estore we display the details as we received in the Enrichment and Facet feed. Since the details n the feed received with Simple text, hence the same is displayed on Estore. | This is not an issue as it is not a part of the requirement. | Raul will Review with the team in charge (oscar) . This was reviewed with business and this will be include in next release once is a new requirement | parking lot | Provide review status. ETA: 25-Ago (arturo y Raul) | Tendremos estatus al regreso de Arturo | No se ha platicado con Arturo y falta feed texto
2 | Some items are showing the promotion icons twice | Sol | 2016-07-26 | Medium | 2016-07-27 | Closed | Walmex | Two promotions are active for the same product : 00000347371 and 00000347372. Hence 2 images are displayed on Estore | This is due to wrong mapping of promotions to the UPC | Review scenarios to have an automatically process
3 | After typing in the user and password (incorrectly) the user account is not getting blocked after 3 times | Chris | 2016-07-26 | Medium | 2016-07-27 | Closed |  | This as per the requirements. User account should not get blocked after invalid retires | This is not an issue as it is not a part of the requirement. | Closed
4 | You enter product lines and leaving huge | Amado | 2016-07-26 |  | Not Available | Duplicate | Wipro | This is also observed when #5 is seen | This issue is a part of issue #5.
5 | You can not click on the links menu | Amado | 2016-07-26 |  | Not Available | Re-Opened | Oracle/Wipro | Work In Progress. Oracle SR is raised. 29: AUG Fix is deployed in Production 30 AUG: We were able to reproduct the issue, but on Page re-load the issue is not seen. |  | Oracle/Wipro to Provide an ETA |  | Sttoper, Raul will provide ETA on 24 Ago. Status 24-Aug: There is still in progress no ETA yet | There are no new status | Retest today and it's OK
6 | Today it continues to change the image of red delicious apple in PDP | Amado | 2016-07-26 |  | 2016-07-27 | Closed | Walmex/Oscar | Issue with the set of images received in the image feed for this Product. Already discussed with Oscar | Review with Oscar this point, and escalate. Deparment,family and fineline | Review with Oscar this point, and escalate. Deparment,family and fineline | imagen de familia están en centinel. Extración masiva de universo de imagen de Centinel. Revisar con Roberto Perez quien sube las imágenes. Y después regresamos con Oscar para que se carguen automáticamente. Oscar da la fecha final | Solution will be on 26-Ago | Confirma con Oscar liberación y al final del día confirma entregable | Retest today and it is NOT working properly
7 | I can not set the jump grams in weighable products | Amado | 2016-07-26 |  | 2016-07-27 | Not in requirement |  | Jump is by default 50 grms – as per the requirements. Inorder to have a jump value other than 50, team should configure the Minimum and Average weight accordingly | This is not an issue and was explained to the business team | this is a Feed issue, this will be reviewed with Perla and wipro | New requirement, for review. Revisar con Perla Palacios, para que no se sobre escriba la información desde host. | Raul will review with Perla and Rodrigo, statun on 24-Aug. Status Aug 24: Rodrigo Larios said if this requirement needs to do changes in the feed will take 2 weeks for all implementation cycle. | There are no new status | There are no new status
8 | They were set minimums and maximums for some time, but tell us that if there is a new SKU for UPC that is already configured , you must manually configure this new SKU | Amado | 2016-07-26 |  | 2016-07-27 | Not in requirement |  | This is as per the requirements. We need to configure the Minimum and Average weight at the SKU. | This is not an issue and was explained to the business team | this is a Feed issue, this will be reviewed with Perla and wipro | New requirement, for review. Wipro will review this again | Raul will review status with Perla on 24-Aug. Technical team needs to review this requirement and provide an ETA, today this will be done manually, for business this is not a good solution | There are no new status | There are no new status
9 | Links created show you items that do not correspond | Amado | 2016-07-26 |  | 2016-08-05 | Closed | Walmex | Endeca patch was deployed on 05 AUG in Production. Awaiting walmart team to test and confirm if this issue can be closed | Patch installed in Production Env. No exception happened during staging baseline indexing. Under observation, will be closed once business user confirms. | Is already fixed, business will confirm
10 | Hay artículos que tienen leyenda de Pocas Piezas, ¿cómo se define que esta leyenda se pinte? | Vianey | 2016-07-27 | Medium |  | Closed |  | Details are shared in the Attached email. Based on the Product Type, TH1, TH2 and rules defined Product will be displayed as ‘Pocas Piezas’ or ‘No Disponible’ | This is not an issue and was a request for understanding the concepts which was clarified | Closed by Business
11 | Nos pasó a varios que tienes que estar borrando cookies para que puedas ver banners y carruseles | Amado | 2016-07-27 | High |  | Duplicate |  | It looks to be issue with the PageServer Cache component for taxonomy. Team is working on the issue to understand the root cause and the fix. | This issue is a follow up on issue #5.
12 | De liga creada se ven los artículos pero algunos no muestran foto en PLP pero si en PDP | Rocio | 2016-07-27 | High |  | Duplicate | Walmex | Issue with the set of images received in the image feed for this Product. Already discussed with Oscar | This issue is a part of issue #6.
13 | Hay artículos con la leyenda no disponible, ¿cuál es la regla para que se pinte esta leyenda? | Vianey | 2016-07-27 | Medium |  | Closed |  | Details are shared in the Attached email. Based on the Product Type, TH1, TH2 and rules defined Product will be displayed as ‘Pocas Piezas’ or ‘No Disponible’ | This is not an issue and was a request for understanding the concepts which was clarified
14 | Al dar click a un no disponible, manda pantalla de Banner/ Producto no encontrado |  | 2016-07-27 | Medium |  | Ready For Retest | Walmex | On click of No disponible Product will not navigate to PDP page with producto no encontrado. We should not be seeing this issue today. When checked for the same Product shared in the PPT, product is now not listed in Search Listing page as well. | This issue was not seen when checked and was not reproducible by the business team |  |  | Reopen issue, is still with same beahaivor- 24 Ago | There are no new status | Retest today, issue is was not replicate, need business approval for closing
15 | Busqueda de papel de baño y salen otros artículos | Vianey | 2016-07-27 | High |  | Closed | Walmex | Search tuning to be taken care
16 | I looked up for M&M's, there's 4 results but none are shown on PLP | Raúl / Juls | 2016-07-28 | High |  | Closed | Walmex/Geovanni | This was due to the Search configurations changed in Production Endeca. Configuratiosna are now corrected, we should not be having this issue now | Review in Endeca |  |  | Next status on 24-Ago by Geovanni. Status Aug-24: this issue is still SR open | There are no new status | There are no new status | Closed by Geovanni
17 | UPC: 00780432021408 does not have a photo (on current site it does). Still on ATG instead of showing the walmart spark, we're showing the superama logo. | Vianey | 2016-07-28 | High |  | Duplicate | Walmex | Issue with the set of images received in the image feed for this Product. Already discussed with Oscar | This issue is a part of issue #6. Oscar is working on this issue |  | Open by bussines
18 | I add items into the cart, then remove them from it and the cart is not decreasing the total amount, later I add new items and the cart is not adding to the total amount correctly | Juls | 2016-07-28 | High |  | Closed | Walmex | Issue is fixed and available in Production Env | This is closed as per the verbal confirmation by Amado
19 | Based on our understanding of the recommendations functionality: if there's only a recommendation created to a family on the whole hierarchy, the lower levels would inherit that recommendation. It is not working that way | Raul | 2016-07-29 | High |  | Closed | Walmex | Yes the understanding is correct. if there's only a recommendation created to a family on the whole hierarchy, the lower levels would inherit that recommendation, Provided property 'Default Parent Category' is mapped correctly in BCC at Each Level - Department, Family, fineline and Product. Suspect the issue is seen in case where the Default Parent category is not mapped correct. But for further analysis we need the data points - Family where recommendations were set. Finelin and Product details (Sample) where Recommendatios are not getting displayed
20 | Real order is created #1002780155 (18576185), customer never got email notification | Sol | 2016-08-01 | High |  | Work in Progress | Walmex/Benjamin | Seems to be some issue with sender domain name used in production. Currently the Domain configured is ‘walmex.spitfire@walmart.com.mx’. Please let us know the Sender email can be configured for End user and for Support emails. In QA it is super@walmart.com | These configuration changes are made and it looks to be closed. Need a confirmation from the business team |  |  | Next status on 24-Aug . Status 24-Aug: This issue will be fixed next Aug-29th | There are no new status | There are no new status
21 | Brand facet is not showing properly, as not all brands are visible, once the last visible brand is selected another one appear below that one, this may need to be validated accross different browsers to see if the facet is not being displayed correctly on certainly scenarios and/or browsers | Vianey | 2016-08-01 | Medium |  | Closed | Walmex | Checked and found the issue is with endeca configuration . Maximum refinements for brand is configured as 10 in production. Changed the value to 200 in QA and it lists all the brands. So to fix this is production, shall we modify the same in endeca? | These configuration changes are made and it looks to be closed. Need a confirmation from the business team
22 | When an order is paid using PayPal eStore is not allowing the payment. | Veronica | 2016-08-09 | High |  | Not implemented | Walmex/Pedro | Production Env is currently connected to Paypal SandBox Instance. Paypal Production ENV will be available only after SRCR approval. During this time, Walmex team need to create the profiles in SandBox env for testing |  |  |  | Implementation will be after 29-Aug | There are no new status | There are no new status
23 | On PLP some images has different size | Rocio | 2016-08-11 | Medium |  | Duplicate | Walmex | We have not received the proper image size in the product image feed. Oscar/team need to correct the image size in the Product Image Feed
24 | Promotion Banner Timer is not working properly | Elizabeth | 2016-08-16 | High |  | Closed | Walmex | Promotion Banner Timer is not working, evidence is attached in a separate email 29 AUG: Deployed the Fix in Prodcutuion. Please Verify |  |  |  | Next Status 24-Aug. Status 24-Aug: This will be fixed on next deployment Aug 26th | There are no new status | Retest today, has same status, it si NOT working properly | closed by business
25 | Personal Care section is not shown on eStore | Elizabeth | 2016-08-17 | High |  | Closed | Walmex/Elizabeth | Request Team to select the query again Endeca Experience Manager for this Fineline. Srinivas/Martin can help here.
26 | Images has different size | Vianey | 2016-08-17 | High |  | Duplicate |  | Work In Progress. Oracle SR is raised. Duplicate as #5
27 | When PayPal is selected as payment method, the application redirects to a wrong page | Amado | 2016-08-17 | High |  | Closed | Walmex | Need to understand more on the Flow user has taken. As of now, seems not to be an issue. Martin will check with Amado for the closure | It is the functionality of 'Enable Quick purchase with PayPal'
28 | Item is located in wrong catalog | Amado | 2016-08-18 | High |  | Work in Progress | Walmex/Felix and Perla Palacios | evidence is attached in a separate email | Product status received from Enrichment feed was Blank. Hence the product is not indexed and displayed on Estore. Inorder to get the Product displayed on Estore, We need to update the Product Status |  |  | Next Status 24-Aug. Status 24-Aug: Enrichment feed needs to send to a particular product, is still in progress | There are no new status | There are no new status
29 | review functionality required by business | Amado | 2016-08-23 | High |  | New requirements | Walmex | There are functionality that business wants to include in next releases, this will be reviewed by functional team. ETA: 26-Ago |  |  |  |  | There are no new status | List requested functionalities
30 | If I capture in my eStore comments in order if printed correctly, but are not displayed in the application store in the comments field of the order | Amado | 2016-08-23 | High |  | New | Walmex / Rodrigo and Adrian | Want SE team to check and confirm why the comments are not printed in the customer print |  |  |  |  | Martin is reviewing the issue, provide an answer next Aug 29th | There are no new status
31 | Crear Cuenta. • When you press the button “Crear mi cuenta” intermittently, without entering the e-mail, the system allows passing the register form. • The system allows to pass at the registration form, when you add an e-mail with invalid form, for example: "-----@---.com" • The system doesn’t limit the characters in the e-mail area. • The system doesn’t allow realizing a search from the Login/Create Account screen. • The system allows saving a new direction without specifying your preference store, the system should send to the user, a validation message to the capture of this area. • The system allows to register an account with an invalid phone, for example "1111111111". • The system allows to register an account with an extension phone, for example "1111111111". • The system allows to register an account with an cell phone, for example "1111111111". • The system doesn’t limit the password area like in the production actual version. In the actual system the password must have from 8 to 16 characters. • The system doesn’t limit the extension area like in the actual production version. In the actual system, the extension must have 5 digits. • The system doesn’t limit the cell phone area like in the actual production version. In the actual system, the extension must have 10 digits. • The system allows adding spaces before adding the names facts in the area and these spaces have to reflect in the data edition. • The system allows adding spaces before adding the last name data area, and these spaces have to reflect in the data edition. • When you select the "VER TÉRMINOS Y CONDICIONES" link, in the register form of a new account, the system shows the label "??? profile.termsandconditions.text ???". | Miguel | 2016-08-25 | High |  | As per requirements | Wipro | • The system allows adding spaces before adding the last name data area, and these spaces have to reflect in the data edition. The point highlighted in red needs an additional analysis. It does not affects any functionality. But just to know if there is any additional imporvements that can be done.
32 | Mis Listas. • A lot of of my actual features list didn’t inherit, for example: "Copiar artículos de esta lista a", "Imprimir", "Exportar a excel", "Crear lista". • When add a product to cart, the system shows the message “Superó la cantidad permitida”. • When you rename a list with special characters, the system doesn’t show the list Detail. | Miguel | 2016-08-25 | High |  | As per requirements | Wipro | • When you rename a list with special characters, the system doesn’t show the list Detail. The point highlighted in red needs a fix. |  |  |  |  | Martin is reviewing the issue, provide an answer next Aug 29th | Revisar con Miguel los caracteres y si es stopper
33 | Home. • The system doesn’t adapt correctly to a desktop screen, the Chrome version is: 46.0.2490.80 m | Miguel | 2016-08-25 | High |  | Closed | Walmex/Miguel´s team | This was not reproducible with the same chrome version during the meeting. Team to share further details on how to reproduce this issue. |  |  |  |  | miguel's team will send screenshot, once the issue is not able to reproduce | Se sigue trabajando, no hay fecha
34 | Salsas Caseras category has issues again, cosmetic line is into this category, it is a big mistake | Amado | 2016-08-26 | High |  | Pending Clarification | Walmex/Carolina's team | Added atachment | Carolina's team to confirm if the mapping of these products were done right in BCC. |  |  |  | Sends issue to wipro, we will have first answer next Aug 29th | already review with Juliana, she will provide status
35 | Into Home header shows additional characters (strange characters) | Raul Fernando | 2016-08-29 | High |  | Ready For Retest | Walmex/Amado/Wipro | Added atachment 30 AUG: We have tried replicating the issue, but failed. We request Amado to show the isus eto Srini/Sudeep as soon as it is seen, meanwhile wipro team will try to reproduce in production
21
,

## Summ CSC Closed
Issue No. | Description | Reporter | Reported | Criticality | Due Date | Status | Owner
1 | "Recoge en tienda" Or pick up at the store is not going through if we select the option. | Mario | 2016-08-15 | High |  | Closed | Jesus
2 | Payment options are retricted to one per order | Mario | 2016-08-15 | High |  | Closed | Walmex/Arturo
3 | The bill options are not correct. | Mario | 2016-08-15 | High |  | Closed | Walmex/Arturo
4 | Systems is experimenting slow behaivor | Mario | 2016-08-15 | High |  | Work in Progress | Walmex/Javier
5 | Data from a existing regular customers is no showing up | Valeria | 2016-08-15 | High |  | Open | Wipro
6 | The link is not working through internet explorer | Javier | 2016-08-15 | High |  | Duplicate/Work in Progress
7 | Surcharge from home delivery it´s wrong | Mario y Javier | 2016-08-15 | High |  | Closed | Walmex
8 | The catalog is incomplete. | Mario y Javier | 2016-08-15 | High |  | Ready for retest | Jesus
9 | Image from the Item isn´t available | Mario y Javier | 2016-08-15 | High |  | Closed | Walmex
10 | We cant apply the promotions | Mario y Javier | 2016-08-15 | High |  | Ready for retest | Jesus
11 | Current promos are not avalaible | Mario y Javier | 2016-08-15 | High |  | Ready for retest | Jesus
12 | Comment on the order are not avialble just until the order its printed | Mario y Javier | 2016-08-15 | High |  | Work in Progress | Walmex/Super Entrega
13 | Order is not availbale | Mario y Javier | 2016-08-15 | High |  | Closed | Walmex
14 | CSC have the wrong Postal codes | Mario y Javier | 2016-08-15 | High |  | Ready for retest | Walmex/Perla
15 | Uploaded catalog is not working properly | Mario y Javier | 2016-08-15 | High |  | Ready for retest | Walmex/Jesus
16 | All the items are as not available | Mario y Javier | 2016-08-15 | High |  | Closed | Walmex/Jesus
17 | The weighing is not right | Mario y Javier | 2016-08-15 | High |  | Ready for retest | Walmex/Arturo
18 | We add certain amount of items and at the end , we are missing some of them | Mario y Javier | 2016-08-15 | High |  | Closed | Walmex
8

## eStore
Issue No. | Description | Reporter | Reported | Criticality | Due Date | Status | Owner | Comments | Additional Comments | Comments with business | 2016-08-16 | 2016-08-23 | 2016-08-26 | 2016-08-29 | 2016-08-30
1 | Some words on eStore that should be shown in bold font, links are not shown properly | Item File | 2016-07-26 | Medium | 2016-07-27 | Not in requirement | Oscar / Arturo | For ATG Estore we display the details as we received in the Enrichment and Facet feed. Since the details n the feed received with Simple text, hence the same is displayed on Estore. | This is not an issue as it is not a part of the requirement. | Raul will Review with the team in charge (oscar) . This was reviewed with business and this will be include in next release once is a new requirement | parking lot | Provide review status. ETA: 25-Ago (arturo y Raul) | Tendremos estatus al regreso de Arturo | No se ha platicado con Arturo y falta feed texto
2 | Some items are showing the promotion icons twice | Sol | 2016-07-26 | Medium | 2016-07-27 | Closed | Walmex | Two promotions are active for the same product : 00000347371 and 00000347372. Hence 2 images are displayed on Estore | This is due to wrong mapping of promotions to the UPC | Review scenarios to have an automatically process
3 | After typing in the user and password (incorrectly) the user account is not getting blocked after 3 times | Chris | 2016-07-26 | Medium | 2016-07-27 | Closed |  | This as per the requirements. User account should not get blocked after invalid retires | This is not an issue as it is not a part of the requirement. | Closed
4 | You enter product lines and leaving huge | Amado | 2016-07-26 |  | Not Available | Duplicate | Wipro | This is also observed when #5 is seen | This issue is a part of issue #5.
5 | You can not click on the links menu | Amado | 2016-07-26 |  | 2016-09-12 | Re-Opened | Oracle/Wipro | Work In Progress. Oracle SR is raised. 29: AUG Fix is deployed in Production 30 AUG: We were able to reproduct the issue, but on Page re-load the issue is not seen. |  | Oracle/Wipro to Provide an ETA |  | Sttoper, Raul will provide ETA on 24 Ago. Status 24-Aug: There is still in progress no ETA yet | There are no new status | Retest today and it's OK
6 | Today it continues to change the image of red delicious apple in PDP | Amado | 2016-07-26 |  | 2016-09-05 | Closed | Walmex/Oscar | Issue with the set of images received in the image feed for this Product. Already discussed with Oscar | Review with Oscar this point, and escalate. Deparment,family and fineline | Review with Oscar this point, and escalate. Deparment,family and fineline | imagen de familia están en centinel. Extración masiva de universo de imagen de Centinel. Revisar con Roberto Perez quien sube las imágenes. Y después regresamos con Oscar para que se carguen automáticamente. Oscar da la fecha final | Solution will be on 26-Ago | Confirma con Oscar liberación y al final del día confirma entregable | Retest today and it is NOT working properly
7 | I can not set the jump grams in weighable products | Amado | 2016-07-26 |  | 2016-07-27 | Not in requirement |  | Jump is by default 50 grms – as per the requirements. Inorder to have a jump value other than 50, team should configure the Minimum and Average weight accordingly | This is not an issue and was explained to the business team | this is a Feed issue, this will be reviewed with Perla and wipro | New requirement, for review. Revisar con Perla Palacios, para que no se sobre escriba la información desde host. | Raul will review with Perla and Rodrigo, statun on 24-Aug. Status Aug 24: Rodrigo Larios said if this requirement needs to do changes in the feed will take 2 weeks for all implementation cycle. | There are no new status | There are no new status
8 | They were set minimums and maximums for some time, but tell us that if there is a new SKU for UPC that is already configured , you must manually configure this new SKU | Amado | 2016-07-26 |  | 2016-09-05 | Not in requirement |  | This is as per the requirements. We need to configure the Minimum and Average weight at the SKU. | This is not an issue and was explained to the business team | this is a Feed issue, this will be reviewed with Perla and wipro | New requirement, for review. Wipro will review this again | Raul will review status with Perla on 24-Aug. Technical team needs to review this requirement and provide an ETA, today this will be done manually, for business this is not a good solution | There are no new status | There are no new status
9 | Links created show you items that do not correspond | Amado | 2016-07-26 |  | 2016-08-05 | Closed | Walmex | Endeca patch was deployed on 05 AUG in Production. Awaiting walmart team to test and confirm if this issue can be closed | Patch installed in Production Env. No exception happened during staging baseline indexing. Under observation, will be closed once business user confirms. | Is already fixed, business will confirm
10 | Hay artículos que tienen leyenda de Pocas Piezas, ¿cómo se define que esta leyenda se pinte? | Vianey | 2016-07-27 | Medium |  | Closed |  | Details are shared in the Attached email. Based on the Product Type, TH1, TH2 and rules defined Product will be displayed as ‘Pocas Piezas’ or ‘No Disponible’ | This is not an issue and was a request for understanding the concepts which was clarified | Closed by Business
11 | Nos pasó a varios que tienes que estar borrando cookies para que puedas ver banners y carruseles | Amado | 2016-07-27 | High |  | Duplicate |  | It looks to be issue with the PageServer Cache component for taxonomy. Team is working on the issue to understand the root cause and the fix. | This issue is a follow up on issue #5.
12 | De liga creada se ven los artículos pero algunos no muestran foto en PLP pero si en PDP | Rocio | 2016-07-27 | High |  | Duplicate | Walmex | Issue with the set of images received in the image feed for this Product. Already discussed with Oscar | This issue is a part of issue #6.
13 | Hay artículos con la leyenda no disponible, ¿cuál es la regla para que se pinte esta leyenda? | Vianey | 2016-07-27 | Medium |  | Closed |  | Details are shared in the Attached email. Based on the Product Type, TH1, TH2 and rules defined Product will be displayed as ‘Pocas Piezas’ or ‘No Disponible’ | This is not an issue and was a request for understanding the concepts which was clarified
14 | Al dar click a un no disponible, manda pantalla de Banner/ Producto no encontrado |  | 2016-07-27 | Medium | 2016-09-01 | Ready For Retest | Walmex | On click of No disponible Product will not navigate to PDP page with producto no encontrado. We should not be seeing this issue today. When checked for the same Product shared in the PPT, product is now not listed in Search Listing page as well. | This issue was not seen when checked and was not reproducible by the business team |  |  | Reopen issue, is still with same beahaivor- 24 Ago | There are no new status | Retest today, issue is was not replicate, need business approval for closing
15 | Busqueda de papel de baño y salen otros artículos | Vianey | 2016-07-27 | High |  | Closed | Walmex | Search tuning to be taken care
16 | I looked up for M&M's, there's 4 results but none are shown on PLP | Raúl / Juls | 2016-07-28 | High |  | Closed | Walmex/Geovanni | This was due to the Search configurations changed in Production Endeca. Configuratiosna are now corrected, we should not be having this issue now | Review in Endeca |  |  | Next status on 24-Ago by Geovanni. Status Aug-24: this issue is still SR open | There are no new status | There are no new status | Closed by Geovanni
17 | UPC: 00780432021408 does not have a photo (on current site it does). Still on ATG instead of showing the walmart spark, we're showing the superama logo. | Vianey | 2016-07-28 | High |  | Duplicate | Walmex | Issue with the set of images received in the image feed for this Product. Already discussed with Oscar | This issue is a part of issue #6. Oscar is working on this issue |  | Open by bussines
18 | I add items into the cart, then remove them from it and the cart is not decreasing the total amount, later I add new items and the cart is not adding to the total amount correctly | Juls | 2016-07-28 | High |  | Closed | Walmex | Issue is fixed and available in Production Env | This is closed as per the verbal confirmation by Amado
19 | Based on our understanding of the recommendations functionality: if there's only a recommendation created to a family on the whole hierarchy, the lower levels would inherit that recommendation. It is not working that way | Raul | 2016-07-29 | High |  | Closed | Walmex | Yes the understanding is correct. if there's only a recommendation created to a family on the whole hierarchy, the lower levels would inherit that recommendation, Provided property 'Default Parent Category' is mapped correctly in BCC at Each Level - Department, Family, fineline and Product. Suspect the issue is seen in case where the Default Parent category is not mapped correct. But for further analysis we need the data points - Family where recommendations were set. Finelin and Product details (Sample) where Recommendatios are not getting displayed
20 | Real order is created #1002780155 (18576185), customer never got email notification | Sol | 2016-08-01 | High | 2016-09-07 | Work in Progress | Walmex/Benjamin | Seems to be some issue with sender domain name used in production. Currently the Domain configured is ‘walmex.spitfire@walmart.com.mx’. Please let us know the Sender email can be configured for End user and for Support emails. In QA it is super@walmart.com | These configuration changes are made and it looks to be closed. Need a confirmation from the business team |  |  | Next status on 24-Aug . Status 24-Aug: This issue will be fixed next Aug-29th | There are no new status | There are no new status
21 | Brand facet is not showing properly, as not all brands are visible, once the last visible brand is selected another one appear below that one, this may need to be validated accross different browsers to see if the facet is not being displayed correctly on certainly scenarios and/or browsers | Vianey | 2016-08-01 | Medium |  | Closed | Walmex | Checked and found the issue is with endeca configuration . Maximum refinements for brand is configured as 10 in production. Changed the value to 200 in QA and it lists all the brands. So to fix this is production, shall we modify the same in endeca? | These configuration changes are made and it looks to be closed. Need a confirmation from the business team
22 | When an order is paid using PayPal eStore is not allowing the payment. | Veronica | 2016-08-09 | High | 2016-09-12 | Not implemented | Walmex/Pedro | Production Env is currently connected to Paypal SandBox Instance. Paypal Production ENV will be available only after SRCR approval. During this time, Walmex team need to create the profiles in SandBox env for testing |  |  |  | Implementation will be after 29-Aug | There are no new status | There are no new status
23 | On PLP some images has different size | Rocio | 2016-08-11 | Medium |  | Duplicate | Walmex | We have not received the proper image size in the product image feed. Oscar/team need to correct the image size in the Product Image Feed
24 | Promotion Banner Timer is not working properly | Elizabeth | 2016-08-16 | High |  | Closed | Walmex | Promotion Banner Timer is not working, evidence is attached in a separate email 29 AUG: Deployed the Fix in Prodcutuion. Please Verify |  |  |  | Next Status 24-Aug. Status 24-Aug: This will be fixed on next deployment Aug 26th | There are no new status | Retest today, has same status, it si NOT working properly | closed by business
25 | Personal Care section is not shown on eStore | Elizabeth | 2016-08-17 | High |  | Closed | Walmex/Elizabeth | Request Team to select the query again Endeca Experience Manager for this Fineline. Srinivas/Martin can help here.
26 | Images has different size | Vianey | 2016-08-17 | High |  | Duplicate |  | Work In Progress. Oracle SR is raised. Duplicate as #5
27 | When PayPal is selected as payment method, the application redirects to a wrong page | Amado | 2016-08-17 | High |  | Closed | Walmex | Need to understand more on the Flow user has taken. As of now, seems not to be an issue. Martin will check with Amado for the closure | It is the functionality of 'Enable Quick purchase with PayPal'
28 | Item is located in wrong catalog | Amado | 2016-08-18 | High |  | Work in Progress | Walmex/Felix and Perla Palacios | evidence is attached in a separate email | Product status received from Enrichment feed was Blank. Hence the product is not indexed and displayed on Estore. Inorder to get the Product displayed on Estore, We need to update the Product Status |  |  | Next Status 24-Aug. Status 24-Aug: Enrichment feed needs to send to a particular product, is still in progress | There are no new status | There are no new status
29 | review functionality required by business | Amado | 2016-08-23 | High |  | New requirements | Walmex | There are functionality that business wants to include in next releases, this will be reviewed by functional team. ETA: 26-Ago |  |  |  |  | There are no new status | List requested functionalities
30 | If I capture in my eStore comments in order if printed correctly, but are not displayed in the application store in the comments field of the order | Amado | 2016-08-23 | High |  | New | Walmex / Rodrigo and Adrian | Want SE team to check and confirm why the comments are not printed in the customer print |  |  |  |  | Martin is reviewing the issue, provide an answer next Aug 29th | There are no new status
31 | Crear Cuenta. • When you press the button “Crear mi cuenta” intermittently, without entering the e-mail, the system allows passing the register form. • The system allows to pass at the registration form, when you add an e-mail with invalid form, for example: "-----@---.com" • The system doesn’t limit the characters in the e-mail area. • The system doesn’t allow realizing a search from the Login/Create Account screen. • The system allows saving a new direction without specifying your preference store, the system should send to the user, a validation message to the capture of this area. • The system allows to register an account with an invalid phone, for example "1111111111". • The system allows to register an account with an extension phone, for example "1111111111". • The system allows to register an account with an cell phone, for example "1111111111". • The system doesn’t limit the password area like in the production actual version. In the actual system the password must have from 8 to 16 characters. • The system doesn’t limit the extension area like in the actual production version. In the actual system, the extension must have 5 digits. • The system doesn’t limit the cell phone area like in the actual production version. In the actual system, the extension must have 10 digits. • The system allows adding spaces before adding the names facts in the area and these spaces have to reflect in the data edition. • The system allows adding spaces before adding the last name data area, and these spaces have to reflect in the data edition. • When you select the "VER TÉRMINOS Y CONDICIONES" link, in the register form of a new account, the system shows the label "??? profile.termsandconditions.text ???". | Miguel | 2016-08-25 | High |  | As per requirements | Wipro | • The system allows adding spaces before adding the last name data area, and these spaces have to reflect in the data edition. The point highlighted in red needs an additional analysis. It does not affects any functionality. But just to know if there is any additional imporvements that can be done.
32 | Mis Listas. • A lot of of my actual features list didn’t inherit, for example: "Copiar artículos de esta lista a", "Imprimir", "Exportar a excel", "Crear lista". • When add a product to cart, the system shows the message “Superó la cantidad permitida”. • When you rename a list with special characters, the system doesn’t show the list Detail. | Miguel | 2016-08-25 | High |  | As per requirements | Wipro | • When you rename a list with special characters, the system doesn’t show the list Detail. The point highlighted in red needs a fix. |  |  |  |  | Martin is reviewing the issue, provide an answer next Aug 29th | Revisar con Miguel los caracteres y si es stopper
33 | Home. • The system doesn’t adapt correctly to a desktop screen, the Chrome version is: 46.0.2490.80 m | Miguel | 2016-08-25 | High |  | Pending Clarification | Walmex/Miguel´s team | This was not reproducible with the same chrome version during the meeting. Team to share further details on how to reproduce this issue. |  |  |  |  | miguel's team will send screenshot, once the issue is not able to reproduce | Se sigue trabajando, no hay fecha
34 | Salsas Caseras category has issues again, cosmetic line is into this category, it is a big mistake | Amado | 2016-08-26 | High | 2016-09-02 | Pending Clarification | Walmex/Carolina's team | Added atachment | Carolina's team to confirm if the mapping of these products were done right in BCC. |  |  |  | Sends issue to wipro, we will have first answer next Aug 29th | already review with Juliana, she will provide status
35 | Into Home header shows additional characters (strange characters) | Raul Fernando | 2016-08-29 | High | 2016-09-01 | Ready For Retest | Walmex/Amado/Wipro | Added atachment 30 AUG: We have tried replicating the issue, but failed. We request Amado to show the isus eto Srini/Sudeep as soon as it is seen, meanwhile wipro team will try to reproduce in production
36 | there are more items in ATG catalog than current system Catalog | Amado | 2016-09-01 | High |  | Pending Clarification | Walmex/Amado | 07 SEP: Please confrim if the discussion is being done and is there any other concern on this issue
37 | Deploys to Endeca Production is not working properly | Elizabeth | 2016-09-02 | High |  | New | Wipro / Oracle
,

## CSC
Issue No. | Description | Reporter | Reported | Criticality | Due Date | Status | Owner | Comments | additional Comments | Comments with business | 2016-08-23
1 | "Recoge en tienda" Or pick up at the store is not going through if we select the option. | Mario | 2016-08-15 | High |  | Closed | Jesus | Service is not available for our customer and freezes at the time that we try to select a slot | To be Retested in IE8 and confirm back Also please note Agent needs to select the Store option from the Shipping page to see Store Pickup payment options on later screens
2 | Payment options are retricted to one per order | Mario | 2016-08-15 | High |  | Closed | Walmex/Arturo | Previous CRM aloud us to select diferent payment opts on the order, per customer request. | Partial payment method is not a part of the requirement. Refer JIIRA ID: | There should be option for multiple payments. | Parking Lot. Se incluye el requerimiento para un release posterior
3 | The bill options are not correct. | Mario | 2016-08-15 | High |  | Closed | Walmex/Arturo | Extra information is required whenever the customer ask for the bill , the options are incorrect. | Please Note billing address or invoice address was not part of the spitfire requirements. Refer JIIRA ID: | Need to recheck on the requirements as this is really necessary.
4 | Systems is experimenting slow behaivor | Mario | 2016-08-15 | High |  | Work in Progress | Walmex/Javier | Takes from 5 to 15 minutes to actually change from screen to screen. | 19 AUG: When checked the CSC performance from the Location where martin/Srini are available, CSC page is loading in less than 5 seconds. We request raul/Javier to check on the Walmart Network from Mario's location |  | Network team is working to have better network performance. ETA: 31-Aug
5 | Data from a existing regular customers is no showing up | Valeria | 2016-08-15 | High | 2016-09-12 | Open | Wipro | The store can´t identify a test order from a real one | Unable to search users with First name and Last Name fields. | Jesus to share the db related info on Current Customer care service. | review deep detail
6 | The link is not working through internet explorer | Javier | 2016-08-15 | High |  | Duplicate/Work in Progress |  | Use work , no is not and we are currently using Chrome to do the testing. | The issue still persist. We assume that this is due to the slowness of the network. Duplicated to issue#4
7 | Surcharge from home delivery it´s wrong | Mario y Javier | 2016-08-15 | High |  | Closed | Walmex | Te surcharge is $49 pesos and we currently have $44 pesos, shoulkd be changed. | This is functioning properly as per the feed received. | Martin to share datails from Perla | do more testing. Jesus send the test 24-Aug
8 | The catalog is incomplete. | Mario y Javier | 2016-08-15 | High | 2016-09-02 | Closed | Jesus | Basic stuff is not available , regular products that our customers request | Need details on product and stores. |  | Review deep detail with wipro. 24-Aug
9 | Image from the Item isn´t available | Mario y Javier | 2016-08-15 | High |  | Closed | Walmex | Image shpuld be avaible to comply with the right Item , entire order could be cancel if we send the wrong products | The walmart default images are getting displayed for the UPC for which images feeds are not available. |  | Jesus will share the UPCs where there is discrepancy between eStore and CSC. Solution on 26-Aug
10 | We cant apply the promotions | Mario y Javier | 2016-08-15 | High | 2016-09-02 | Closed | Jesus | We add a promo that is not reflected at the end. | Need few UPC examples to check if Business team has created the promotion in BCC We checked on the few items with promotions and were able to see Promotion getting applied | The products which Jesus has shared has promotion in Current Customer care centre and interim site. But they are not coming via feeds and they are not created in BCC. | Jesus to retest once Amado shares the list of promotions created. 24-Aug
11 | Current promos are not avalaible | Mario y Javier | 2016-08-15 | High | 2016-09-02 | Closed | Jesus | Affect the cross sell thart we coul apply on the every call if is not visible for the sales rep. | We display the cross sell promotions in Full cart page - 'Examinar todos las Promociones'. This is as per CSC Out of the Box. Martin/Srini can help more on this |  | Amado envia ejemplos a Jesus y se vuelve a probar. 24-Aug
12 | Comment on the order are not avialble just until the order its printed | Mario y Javier | 2016-08-15 | High |  | Work in Progress | Walmex/Super Entrega | The store can´t identify a test order from a real one | The comments (Order level and order line comments) are not received at the store side We see the item level and order level comments are available in the order. Can SE team check and confirm why the comments are not printed in Customer print |  | Jesus to retest with another order and confirm on the issues with respect to the comments. 24-Aug
13 | Order is not availbale | Mario y Javier | 2016-08-15 | High |  | Closed | Walmex | Previous CRM aloud us to cuantify and observe previous orders set up by every users. | 22 AUG: Please refer the screen shot shared ,where the CSC agent can search for the orders with different status ad dates | Need to know of the option to see all the orders placed for a particular day by specific agent | This is not an out of the box functionality and it is not a part of the requirement.
14 | CSC have the wrong Postal codes | Mario y Javier | 2016-08-15 | High | 2016-09-02 | Ready for retest | Walmex/Perla | We select a regular location to send an order that won´t go through caude is says that we have no coverage on the area | 19 AUG: Need Business team to check on the Zipcode-Store-Colony-Amt id feed provided to us. As there as no Store received for the zipcode in issue hence we display this error on CSC |  | Provide status 24-Aug
15 | Uploaded catalog is not working properly | Mario y Javier | 2016-08-15 | High | 2016-09-02 | Ready for retest | Walmex/Jesus | Regular item as milk already uploaded on the system is not working for us, we cant added tyo the shoipping cart | We see Keyboard Search is working. Please verify in IE8
16 | All the items are as not available | Mario y Javier | 2016-08-15 | High |  | Closed | Walmex/Jesus | Orders can´t be made | We see Keyboard Search is working. Please verify in IE8
17 | The weighing is not right | Mario y Javier | 2016-08-15 | High | 2016-09-02 | Ready for retest | Walmex/Arturo | We add a certain weight and the system change to a diferent one . | This is as per requirement of minimum weight and average weight. Business to comment on the cases if the customer is so specific on the quantity he/she demands |  | Jesus envía un ejemplo para seguir el issue 24-Aug
18 | We add certain amount of items and at the end , we are missing some of them | Mario y Javier | 2016-08-15 | High |  | Closed | Walmex | We add certain amount of items and at the end , we are missing some of them | This is as per requirement of PIP |  | Validar las reglas de host con Perla

## Mobile
Issue No. | Test Case | Test Case Description | Reporter | Reported | Criticality | Due Date | Status | Owner | Comments | Additional Comments
1 | Validate "Splash" start | Validate "splash" start appears into the app | Christian | 2016-09-06 | Medio |  | New | Joel | "splash" Start is not appear when app is open
2 | PLP | Validate item pictures and descriptions into PLP | Christian | 2016-09-06 | Medio |  | New | Joel | some items descriptions shown in capital letters and no picture, Ex. 00750620580924
3 | PDP | Show related items protected image | Christian | 2016-09-06 | Medio |  | New | Joel | No se muestran las imágenes de protección en Artículos Relacionados
4 | PLP | Validate search by text | Christian | 2016-09-06 | Medio |  | New | Joel | Al realizar la búsqueda de "agua" en resultados de búsqueda aparece el "Despachador Royal Rojo" como agregado a carrito cuando el mismo está vacío
5 | PLP | validate item, price, picture and description | Christian | 2016-09-06 | Medio |  | New | Joel | Aparece campo de rollback con precios de formato diferente ($12.9) y al hacer scroll down se mantiene el ícono de carga de más productos
6 | Open Cart | Open cart after log in | Christian | 2016-09-06 | Alto |  | New | Joel | Carrito queda cargando y no abre, al querer realizar y guardar cualquier acción / cambio mientras carrito se carga app se cierra inesperadamente
7 | Show previous orders | Validate previous orders migration | Christian | 2016-09-06 | Alto |  | New | Joel | App solo muestra pedidos anteriores realizados con versión ATG
8 | Previous orders status | validate previous orders | Christian | 2016-09-06 | Bajo |  | New | Joel | App muestra status de "Cobrado", en general muestra estatus distintos a producción
9 | Buy "most buyed items" | Buy "most buyed items" | Christian | 2016-09-06 | Alto |  | New | Joel | No es posible realizar la compra de "Artículos Más Comprados", al hacer click sobre uno de ellos app hace crash
10 | PLP | Validate Lines | Christian | 2016-09-06 | Medio |  | New | Joel | Al seleccionar una línea de productos desde categorías en súper de manera intermitente y aleatoria abre línea incorrecta que contiene tortillas y otros artículos que no coinciden a la esperada.
11 | Show previous orders | Validate previous orders | Christian | 2016-09-06 | Bajo |  | New | Joel | Aleatoriamente se ven duplicados los pedidos anteriores, mismo número de pedido.
12 | Open App | app start | Christian | 2016-09-06 | Alto |  | New | Joel | La App no abrió, se quedó en color azul, después de 2 min es necesario salir y volver a entrar
13 | Search | Search items by text | Christian | 2016-09-06 | Medio |  | New | Joel | Se tiene que escribir el nombre exacto para que encuentre el producto.
14 | Account Information | Create new account using current email account | Christian | 2016-09-06 | Bajo |  | New | Joel | Te avisa que el correo ya existe después de llenar toda la info de direcciones
15 | Open "My Lists" | Open lines when log in | Christian | 2016-09-06 | Alto |  | New | Joel | Se quedó pensando y no abrió las listas. Es necesario cerrar la aplicación.
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
,